## Sequence Diagram
SEQUENCE DIAGRAM OF CASA de MUEBLES
|  | User: Employee |  | System:Login |  | System:Marketing/SalesHomePage |  | System: Sales Report |  | System: Events List |  | System: Clients List |  | System: TRACKITEM |  |  | System: Marketing Report
LOGS IN
|  |  | PW and UN Verification() |  | bringtoDept(Marketing/Sales HomePage)
bringToProcedure(SalesReport)
bringToProcedure(EventsList)
bringToProcedure(ClientsLIst)
bringToProcedure(TrackItem)
bringToProcedure(MarketingReport)
Import(EVENTSLIST)

## Risk Management
RISK TABLE FOR CASA de MUEBLES SOFTWARE
TOTAL COSTING OF PROJECT: | 200000 | PESOS
RISK | CATEGORY | PROBABILITY | IMPACT | RISK EXPOSURE | POINTER TO RMMM
Down Network | Software risk | 50% | 3 not really a problem since this can be caused by server side of client not by software. But backups and automatic saving should be issued to ensure no data loss. | 100000 | Automatic Saving and backup recovery should be avaialble in the system. Sytem backups should be made regulary as to ensure 0 data loss
Insufficient Databases | Software risk | 50% | 4 - less likely to happen since additional databases are already discussed during department immersion. Revisions on databases could be done quarterly in case needed. | 100000 | additional storage should be alotted for future improvements on program.
Error on LOG-IN Systems | Software risk | 50% | 2 will cause a higher problem since this may hold the business transaction and will occur loss for the company. | 100000 | Automatic Saving and backup recovery should be avaialble in the system. Sytem backups should be made regulary as to ensure 0 data loss
Discrepancy on software per dapartment | Software risk | 80% | 2 - the execution of the programmer assigned per department may have a different approach that may not be able to work properly on main frame | 160000 | Project Managers should regulate a formal way of programming for an efficient merge of softwares. However, suggestions on project should always be welcomed.
Security breached | Software risk | 50% | 1 - very crucial as this will leak company info and also sabotage | 100000 | Security or software should be given a priority and backup measures are also foreseen. Also, security assesments should be made on software developing to avoid such problems.
Unrecoverable databases | Software risk | 50% | 3 - likely to happen but backups should be always available for this purpose | 100000 | Regular testing should be done on software to ensure the productibility of the program.
Software is not supported by Clients Computers | Software risk | 50% | 1 - very crucial since the software may not work properly or at all and will cause loss of money and resources for both client and programmers | 100000 | Before program development, ensure a thorough research in clients sepcifications and environment.
Inefficient Programmers and Heads | Project Risk | 50% | 3 - likely to happen but can easily be solved by hiring more efficient employees. | 100000 | Regular Employee Evaluation is to be done. Outsourcing should always be an option.
Deadlines aren't met | Project Risk | 50% | 2 - Late on deadlines will cause setbacks and will pull the overall project down. Proper delegation of task should be practiced. | 100000 | Project Manager should make it to a point to regularly check on employees perfomance to enhance employees capabilities.
Inadequate resources/manpower | Project Risk | 50% | 1 - crucial for both client and programmer as no business may occur. | 100000 | Before the start of project, the delegation of tasks should already be made. Contingency plans for insufficient /resigining employees should be made. Outsource when needed.
Slow Software | Software risk | 50% | 4 - not really a problem as this should be overseen by the programmer and make necessary improvements or counter-measures. | 100000 | Check technological capabilities of clients and partner software to it. Suggest softwares for best program output.
Software is not working properly | Software risk | 50% | 1 - crucial as software may not act its purpose or not work at all. | 100000 | Test, Test and test. Do regular checkups and backups incase re-installation is required.
Bug in Software | Software risk | 50% | 3 - regular backups for the program are necessary and required. | 100000 | Test, Test and test.
Software is not easily understandable | Project Risk | 80% | 3 - coming from different backgrounds, software should be user-friendly. | 160000 | Immerse with the employees and their capabilities if possible. If not, create trainings and seminars for them to easily understand the software.
Client will not pay / does not push through with the project | Business Risk | 50% | 1 - crucial as this may cost money and resources | 100000 | State in the contract the possible consequences if this situtaion ocurs.
1520000